## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 3 | Iyas K | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 3 | Muhammed Sinan | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Norah Elizabeth Biju | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Bhogyam venkata sai Likhitha | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Ogeti Aravind | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Mahesh D | DevOps Engineer | Week 2 | Yes

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | Linux & AWS Overview | 2026-02-17 | 2026-02-18 | Understanding Linux commands and AWS Services
Sprint 2 | EC2 Instances & VPC | 2026-02-19 | 2026-02-20 | Hands‑on with EC2 and VPC
Sprint 3 | Load Balancers,Subnets, Internet Gateways & NAT Gateways | 2026-02-21 | 2026-02-23 | Setting Up Load Balancers,Public/Private Subnets with IGW & NAT Gateways
Sprint 4 | RDS & 3-Tier Devops Architecture | 2026-02-24 | 2026-02-25 | Fullstack Monolithic App with Frontend, Backend & RDS in 3-Tier Devops Architecture
Sprint 5 | DevOps Worflow, Hardware Level Virtualization and Containerization | 2026-02-26 | 2026-03-02 | Understanding Devops Worflow, hardware virtualization concepts, disadvantages of VMs and Docker Containerization
Sprint 6 | Docker Networking and Compose | 2026-03-03 | 2026-03-04 | Creating containers and images, custom network
|  | 2026-03-05 | 2026-03-05 | Module 1 evaluation presentation
Sprint 7 | Docker disadvantages and docker swarm | 2026-03-06 | 2026-03-07 | Understanding the disadvantages of Docker containers, and the limitations in Docker Swarm
Sprint 8 | Kubernetes Components and Introduction | 2026-03-09 | 2026-03-11 | Understanding the Kubernetes components, its architecture, how components communicate, api server, setting up our own clusters, deep diving into the workflow behind each command of creating control plane, pods and its life cycle.
Sprint 9 | Implementation of Replicaset, Deployment ans services | 2026-03-12 | 2026-03-14 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart
Sprint 10 | Explore configmap, secrets and Metrics server, expose application | 2026-03-16 | 2026-03-18 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB
Sprint 11 | Explore API Gateway, Gateway API and K-Gateway | 2026-03-19 | 2026-03-19 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute.
Sprint12 | Explore GatewayAPI Advanced Topics | 2026-03-23 | 2026-03-23 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services.
Sprint13 | Kubernetes Volumes | 2026-03-24 | 2026-03-25 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting.

## Task_Tracking(23-02)
Sprint | Team | TaskID | Description | AssignedTo | StoryPoint | Status | Reviewer
Sprint 1 | Team 3 | T1-001 | Understand Linux commands and AWS Services | Iyas K | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-002 | Understand Linux commands and AWS Services | Muhammed Sinan | 2 | Done | Norah Elizabeth Biju
Sprint 1 | Team 3 | T1-003 | Understand Linux commands and AWS Services | Norah Elizabeth Biju | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-004 | Understand Linux commands and AWS Services | Bhogyam venkata sai Likhitha | 2 | Done | Mahesh D
Sprint 1 | Team 3 | T1-005 | Understand Linux commands and AWS Services | Ogeti Aravind | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-006 | Understand Linux commands and AWS Services | Mahesh D | 2 | Done | Iyas K
Sprint 2 | Team 3 | T2-001 | Set up EC2 Instances , Configure VPC & Security groups | Iyas K | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-002 | Set up EC2 Instances , Configure VPC & Security groups | Muhammed Sinan | 3 | Done | Ogeti Aravind
Sprint 2 | Team 3 | T2-003 | Set up EC2 Instances , Configure VPC & Security groups | Norah Elizabeth Biju | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-004 | Set up EC2 Instances , Configure VPC & Security groups | Bhogyam venkata sai Likhitha | 3 | Done | Muhammed Sinan
Sprint 2 | Team 3 | T2-005 | Set up EC2 Instances , Configure VPC & Security groups | Ogeti Aravind | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-006 | Set up EC2 Instances , Configure VPC & Security groups | Mahesh D | 3 | Done | Norah Elizabeth Biju
Sprint 3 | Team 3 | T3-001 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Iyas K | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-002 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Muhammed Sinan | 4 | Done | Mahesh D
Sprint 3 | Team 3 | T3-003 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Norah Elizabeth Biju | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-004 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Bhogyam venkata sai Likhitha | 4 | Done | Iyas K
Sprint 3 | Team 3 | T3-005 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Ogeti Aravind | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-006 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Mahesh D | 4 | Done | Bhogyam venkata sai Likhitha
Sprint 4 | Team 3 | T4-001 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Iyas K | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-002 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Muhammed Sinan | 6 | Done | Norah Elizabeth Biju
Sprint 4 | Team 3 | T4-003 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Norah Elizabeth Biju | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-004 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Bhogyam venkata sai Likhitha | 6 | Done | Mahesh D
Sprint 4 | Team 3 | T4-005 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Ogeti Aravind | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-006 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Mahesh D | 6 | Done | Iyas K
Sprint 5 | Team 3 | T5-001 | Create Container and deployed image for monolithic application | Iyas K | 4 | Done | Iyas K
Sprint 5 | Team 3 | T5-002 | Create Container and deployed image for monolithic application | Muhammed Sinan | 4 | Done | Trainer
Sprint 5 | Team 3 | T5-003 | Create Container and deployed image for monolithic application | Norah Elizabeth Biju | 4 | Done | Norah Elizabeth Biju
Sprint 5 | Team 3 | T5-004 | Create Container and deployed image for monolithic application | Bhogyam venkata sai Likhitha | 4 | Done | Trainer
Sprint 5 | Team 3 | T5-005 | Create Container and deployed image for monolithic application | Ogeti Aravind | 4 | Done | Mahesh D
Sprint 5 | Team 3 | T5-006 | Create Container and deployed image for monolithic application | Mahesh D | 4 | Done | Trainer
Sprint 6 | Team 3 | T6-001 | Created custom network and deplyed microservices in multiple containers | Iyas K | 5 | Done | Mahesh D
Sprint 6 | Team 3 | T6-002 | Created custom network and deplyed microservices in multiple containers | Muhammed Sinan | 5 | Done | Trainer
Sprint 6 | Team 3 | T6-003 | Created custom network and deplyed microservices in multiple containers | Norah Elizabeth Biju | 5 | Done | Ogeti Aravind
Sprint 6 | Team 3 | T6-004 | Created custom network and deplyed microservices in multiple containers | Bhogyam venkata sai Likhitha | 5 | Done | Trainer
Sprint 6 | Team 3 | T6-005 | Created custom network and deplyed microservices in multiple containers | Ogeti Aravind | 5 | Done | Muhammed Sinan
Sprint 6 | Team 3 | T6-006 | Created custom network and deplyed microservices in multiple containers | Mahesh D | 5 | Done | e
Sprint 7 | Team 3 | T7-001 | Containerized microservice application with services in two different network and initialized a gateway for communication | Iyas K | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-002 | Containerized microservice application with services in two different network and initialized a gateway for communication | Muhammed Sinan | 5 | Done | Mahesh D
Sprint 7 | Team 3 | T7-003 | Containerized microservice application with services in two different network and initialized a gateway for communication | Norah Elizabeth Biju | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-004 | Containerized microservice application with services in two different network and initialized a gateway for communication | Bhogyam venkata sai Likhitha | 5 | Done | Iyas K
Sprint 7 | Team 3 | T7-005 | Containerized microservice application with services in two different network and initialized a gateway for communication | Ogeti Aravind | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-006 | Containerized microservice application with services in two different network and initialized a gateway for communication | Mahesh D | 5 | Done | Bhogyam venkata sai Likhitha
Sprint 8 | Team 3 | T8-001 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Iyas K | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-002 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Muhammed Sinan | 6 | Done | Norah Elizabeth Biju
Sprint 8 | Team 3 | T8-003 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Norah Elizabeth Biju | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-004 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Bhogyam venkata sai Likhitha | 6 | Done | Mahesh D
Sprint 8 | Team 3 | T8-005 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Ogeti Aravind | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-006 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Mahesh D | 6 | Done | Iyas K
Sprint 9 | Team 3 | T9-001 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Iyas K | 7 | Done | Mahesh D
Sprint 9 | Team 3 | T9-002 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Muhammed Sinan | 7 | Done | Trainer
Sprint 9 | Team 3 | T9-003 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Norah Elizabeth Biju | 7 | Done | Ogeti Aravind
Sprint 9 | Team 3 | T9-004 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Bhogyam venkata sai Likhitha | 7 | Done | Trainer
Sprint 9 | Team 3 | T9-005 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Ogeti Aravind | 7 | Done | Muhammed Sinan
Sprint 9 | Team 3 | T9-006 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Mahesh D | 7 | Done | Norah Elizabeth Biju
Sprint 10 | Team 3 | T10-001 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Iyas K | 8 | Done | Mahesh D
Sprint 10 | Team 3 | T10-002 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Muhammed Sinan | 8 | Done | Trainer
Sprint 10 | Team 3 | T10-003 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Norah Elizabeth Biju | 8 | Done | Ogeti Aravind
Sprint 10 | Team 3 | T10-004 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Bhogyam venkata sai Likhitha | 8 | Done | Trainer
Sprint 10 | Team 3 | T10-005 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Ogeti Aravind | 8 | Done | Muhammed Sinan
Sprint 10 | Team 3 | T10-006 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Mahesh D | 8 | Done | Norah Elizabeth Biju
Sprint 11 | Team 3 | T11-001 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Iyas K | 8 | Done | Trainer
Sprint 11 | Team 3 | T11-002 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Muhammed Sinan | 8 | Done | Norah Elizabeth Biju
Sprint 11 | Team 3 | T11-003 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 11 | Team 3 | T11-004 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Bhogyam venkata sai Likhitha | 8 | Done | Mahesh D
Sprint 11 | Team 3 | T11-005 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Ogeti Aravind | 8 | Done | Trainer
Sprint 11 | Team 3 | T11-006 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Mahesh D | 8 | Done | Bhogyam venkata sai Likhitha
Sprint 12 | Team 3 | T12-001 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Iyas K | 6 | Done | Trainer
Sprint 12 | Team 3 | T12-002 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Muhammed Sinan | 6 | Done | Ogeti Aravind
Sprint 12 | Team 3 | T12-003 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Norah Elizabeth Biju | 6 | Done | Trainer
Sprint 12 | Team 3 | T12-004 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Bhogyam venkata sai Likhitha | 6 | Done | Muhammed Sinan
Sprint 12 | Team 3 | T12-005 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Ogeti Aravind | 6 | Done | Trainer
Sprint 12 | Team 3 | T12-006 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Mahesh D | 6 | Done | Norah Elizabeth Biju
Sprint 13 | Team 3 | T13-001 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Iyas K | 7 | Done | Trainer
Sprint 13 | Team 3 | T13-002 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Muhammed Sinan | 7 | Done | Mahesh D
Sprint 13 | Team 3 | T13-003 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Norah Elizabeth Biju | 7 | Done | Trainer
Sprint 13 | Team 3 | T13-004 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Bhogyam venkata sai Likhitha | 7 | Done | Iyas K
Sprint 13 | Team 3 | T13-005 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Ogeti Aravind | 7 | Done | Trainer
Sprint 13 | Team 3 | T13-006 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Mahesh D | 7 | Done | Bhogyam venkata sai Likhitha

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | CI/CD Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -