## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 4 | MUVVALA VENKATA NAGA SAI AKASH | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Ashutosh Kumar | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | M Vignesh | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 4 | Dhanigasree S | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Suwetha Balasundaram | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Elzabeth Lalson | DevOps Engineer | Week 1 | No

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | Deploying a monolithic application | 2013-02-23 | 2020-02-26 | Deploying an app in EC2 instance where web app and backend and Database is deployed in public, private and RDS respectively
Sprint 2 | Deploying a microservices architecture application | 2026-02-25 | 2026-02-26 | Change the app into a micro service architecture and and deploy it using EC2 and RDS
Sprint 3 | Creating our own Docker images using docker build | 2026-02-26 | 2026-02-28 | Creating our own docker image
Sprint 4 | Implemeted multi tier applications across different containers using host gateway | 2026-03-02 | 2026-03-03 | Work in multi tier app using host gateway
Sprint 5 | IImplemeted multi tier applications across different containers using custome network and stored backups using volumes | 2026-03-03 | 2026-03-04 | Work in multi tier app using networks and volumes
Sprint 6 | Familiarised with Docker swarm and with basic of kubernetes | 2026-03-05 | 2026-03-07 | Familiarised with docker swarm and reasons we need kubernetes and with basics of kubernetes
Sprint 7 | Deploying simple pods in cluster | 2026-03-09 | 2026-03-11 | Deploying simple pods in cluster and understand how the response is happening
Sprint 8 | Worked on deploying applications using ReplicaSet, Deployment, and Services; followed manifest rules; implemented rollout and rollback strategies. | 2026-03-12 | 2026-03-14 | Implemented Metrics Server, Horizontal Pod Autoscaler, resource requests and limits; configured ConfigMaps, Secrets, and HAProxy for scaling.
Sprint 9 | Created YAML manifests, successfully deployed applications, validated rollout and rollback functionality, ensured stable and version-controlled deployments. | 2026-03-16 | 2026-03-18 | Enabled auto scaling (scale up/down), configured application settings securely, validated performance, and ensured efficient resource utilization
Sprint 10 | Implemented HAProxy setup | 2026-03-18 | 2026-03-19 | Understood and implemented HAProxy setup from a separate EC2 instance to access the application. Worked on Horizontal Pod Autoscaling (HPA) including scaling up and scaling down of pods based on load.
Sprint 11 | Explore GatewayAPI Advanced Topics | 2026-03-19 | 2026-03-23 | Gained understanding of API Gateway, Gateway API, and KGateway concepts. Installed and configured KGateway. Successfully exposed the web application using the gateway.
Sprint 12 | Kubernetes Volumes | 2026-03-23 | 2026-03-24 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting.
Sprint 13 | Explored about the kubernetes components | 2026-03-26 | 2026-03-26 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints.
Sprint 14 | Implemented dynamic provisioning using NFS in Kubernetes | 2026-03-27 | 2026-03-27 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB.
Sprint 15 | Implemented Kubernetes StatefulSet Communication & Headless Services | 2026-03-28 | 2026-03-28 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring.
Sprint 16 | Helm Chart Development and Deployment Automation | 2026-03-30 | 2026-03-30 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction.
Sprint 17 | Worked on our own microservices | 2026-03-31 | 2026-04-01 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details.

## Task_Tracking(23-02)
Sprint | Team | TaskID | Description | AssignedTo | StoryPoint | Status | Reviewer
Sprint 1 | Team 4 | T1-001 | Web app deployed properly configuring backend deployment | MUVVALA VENKATA NAGA SAI AKASH | 2 | Done | Trainer
Sprint 1 | Team 4 | T1-002 | Web app deployed properly configuring backend deployment | Ashutosh Kumar | 2 | Done | M Vignesh | Backlog
Sprint 1 | Team 4 | T1-003 | Web app deployed properly configuring backend deployment | M Vignesh | 2 | Done | Trainer
Sprint 1 | Team 4 | T1-004 | Web app deployed properly configuring backend deployment | Dhanigasree S | 2 | Done | Suwetha Balasundaram | To Do
Sprint 1 | Team 4 | T1-005 | Web app deployed properly configuring backend deployment | Suwetha Balasundaram | 2 | Done | Elzabeth Lalson
Sprint 1 | Team 4 | T1-006 | Web app deployed properly configuring backend deployment | Elzabeth Lalson | 2 | Done | Trainer | In Progress
Sprint 2 | Team 4 | T2-001 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | MUVVALA VENKATA NAGA SAI AKASH | 3 | Done | Trainer
Sprint 2 | Team 4 | T2-002 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | Ashutosh Kumar | 3 | Done | M Vignesh | Code Review
Sprint 2 | Team 4 | T2-003 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | M Vignesh | 3 | Done | Trainer
Sprint 2 | Team 4 | T2-004 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | Dhanigasree S | 3 | Done | Suwetha Balasundaram | Done
Sprint 2 | Team 4 | T2-005 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | Suwetha Balasundaram | 3 | Done | Elzabeth Lalson
Sprint 2 | Team 4 | T2-006 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | Elzabeth Lalson | 3 | Done | Trainer | Blocked
Sprint 3 | Team 4 | T3-001 | Creating our own Docker images using docker build | MUVVALA VENKATA NAGA SAI AKASH | 4 | Done | Trainer
Sprint 3 | Team 4 | T3-002 | Creating our own Docker images using docker build | Ashutosh Kumar | 4 | Done | M Vignesh
Sprint 3 | Team 4 | T3-003 | Creating our own Docker images using docker build | M Vignesh | 4 | Done | Trainer
Sprint 3 | Team 4 | T3-004 | Creating our own Docker images using docker build | Dhanigasree S | 4 | Done | Suwetha Balasundaram
Sprint 3 | Team 4 | T3-005 | Creating our own Docker images using docker build | Suwetha Balasundaram | 4 | Done | Elzabeth Lalson
Sprint 3 | Team 4 | T3-006 | Creating our own Docker images using docker build | Elzabeth Lalson | 4 | Done | Trainer
Sprint 4 | Team 4 | T4-001 | Setup RDS & Deploy a 3-Tier Monolithic architecture | MUVVALA VENKATA NAGA SAI AKASH | 6 | Done | Trainer
Sprint 4 | Team 4 | T4-002 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Ashutosh Kumar | 6 | Done | M Vignesh
Sprint 4 | Team 4 | T4-003 | Setup RDS & Deploy a 3-Tier Monolithic architecture | M Vignesh | 6 | Done | Trainer
Sprint 4 | Team 4 | T4-004 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Dhanigasree S | 6 | Done | Suwetha Balasundaram
Sprint 4 | Team 4 | T4-005 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Suwetha Balasundaram | 6 | Done | Elzabeth Lalson
Sprint 4 | Team 4 | T4-006 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Elzabeth Lalson | 6 | Done | Trainer
Sprint 5 | Team 4 | T5-001 | Implemeted multi tier applications across different containers using host gateway | MUVVALA VENKATA NAGA SAI AKASH | 3 | Done | Trainer
Sprint 5 | Team 4 | T5-002 | Implemeted multi tier applications across different containers using host gateway | Ashutosh Kumar | 3 | Done | M Vignesh
Sprint 5 | Team 4 | T5-003 | Implemeted multi tier applications across different containers using host gateway | M Vignesh | 3 | Done | Trainer
Sprint 5 | Team 4 | T5-004 | Implemeted multi tier applications across different containers using host gateway | Dhanigasree S | 3 | Done | Suwetha Balasundaram
Sprint 5 | Team 4 | T5-005 | Implemeted multi tier applications across different containers using host gateway | Suwetha Balasundaram | 3 | Done | Elzabeth Lalson
Sprint 5 | Team 4 | T5-006 | Implemeted multi tier applications across different containers using host gateway | Elzabeth Lalson | 3 | Done | Trainer
Sprint 6 | Team 4 | T6-001 | Familiarised with Docker swarm and with basic of kubernetes | MUVVALA VENKATA NAGA SAI AKASH | 4 | Done | Trainer
Sprint 6 | Team 4 | T6-002 | Familiarised with Docker swarm and with basic of kubernetes | Ashutosh Kumar | 4 | Done | M Vignesh
Sprint 6 | Team 4 | T6-003 | Familiarised with Docker swarm and with basic of kubernetes | M Vignesh | 4 | Done | Trainer
Sprint 6 | Team 4 | T6-004 | Familiarised with Docker swarm and with basic of kubernetes | Dhanigasree S | 4 | Done | Suwetha Balasundaram
Sprint 6 | Team 4 | T6-005 | Familiarised with Docker swarm and with basic of kubernetes | Suwetha Balasundaram | 4 | Done | Elzabeth Lalson
Sprint 6 | Team 4 | T6-006 | Familiarised with Docker swarm and with basic of kubernetes | Elzabeth Lalson | 4 | Done | Trainer
Sprint 7 | Team 4 | T7-001 | Deploying simple pods in cluster | MUVVALA VENKATA NAGA SAI AKASH | 5 | Done | Trainer
Sprint 7 | Team 4 | T7-002 | Deploying simple pods in cluster | Ashutosh Kumar | 5 | Done | M Vignesh
Sprint 7 | Team 4 | T7-003 | Deploying simple pods in cluster | Suwetha Balasundaram | 5 | Done | Trainer
Sprint 7 | Team 4 | T7-004 | Deploying simple pods in cluster | Dhanigasree S | 5 | Done | Suwetha Balasundaram
Sprint 7 | Team 4 | T7-005 | Deploying simple pods in cluster | Suwetha Balasundaram | 5 | Done | Elzabeth Lalson
Sprint 7 | Team 4 | T7-006 | Deploying simple pods in cluster | Elzabeth Lalson | 5 | Done | Trainer
Sprint 8 | Team 4 | T8-001 | Worked on deploying applications using Kubernetes deployment strategie | MUVVALA VENKATA NAGA SAI AKASH | 5 | Done | Elzabeth Lalson
Sprint 8 | Team 4 | T8-002 | Worked on deploying applications using Kubernetes deployment strategie | Ashutosh Kumar | 5 | Done | Suwetha Balasundaram
Sprint 8 | Team 4 | T8-003 | Worked on deploying applications using Kubernetes deployment strategie | M Vignesh | 5 | Done | MUVVALA VENKATA NAGA SAI AKASH
Sprint 8 | Team 4 | T8-004 | Worked on deploying applications using Kubernetes deployment strategie | Dhanigasree S | 5 | Done | Ashutosh Kumar
Sprint 8 | Team 4 | T8-005 | Worked on deploying applications using Kubernetes deployment strategie | Suwetha Balasundaram | 5 | Done | Dhanigasree
sprint 8 | team 4 | T8-006 | Worked on deploying applications using Kubernetes deployment strategie | Elzabeth Lalson | 5 | Done | Suwetha Balasundaram
Sprint 9 | Team 4 | T9-001 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | MUVVALA VENKATA NAGA SAI AKASH | 5 | Done | Trainer
Sprint 9 | Team 4 | T9-002 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | Ashutosh Kumar | 5 | Done | Elzabeth Lalson
Sprint 9 | Team 4 | T9-003 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | M Vignesh | 5 | Done | Ashutosh Kumar
Sprint 9 | Team 4 | T9-004 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | Dhanigasree S | 5 | Done | MUVVALA VENKATA NAGA SAI AKASH
Sprint 9 | Team 4 | T9-005 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | Suwetha Balasundaram | 5 | Done | Trainer
Sprint 9 | Team 4 | T9-006 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | Elzabeth Lalson | 5 | Done | M vignesh
sprint10 | Team 4 | T10-001 | Understood and implemented HAProxy setup from a separate EC2 instance to access the application | MUVVALA VENKATA NAGA SAI AKASH | 4 | Done | Ashutosh Kumar
spritn10 | Team 4 | T10-002 | Understood and implemented HAProxy setup from a separate EC2 instance to access the application | Ashutosh Kumar | 4 | Done | Trainer
spritn10 | Team 4 | T10-003 | Understood and implemented HAProxy setup from a separate EC2 instance to access the application | M Vignesh | 4 | Done | MUVVALA VENKATA NAGA SAI AKASH
spritn10 | Team 4 | T10-004 | Understood and implemented HAProxy setup from a separate EC2 instance to access the application | Dhanigasree S | 4 | Done | Trainer
spritn10 | Team 4 | T10-005 | Understood and implemented HAProxy setup from a separate EC2 instance to access the application | Suwetha Balasundaram | 4 | Done | M vignesh
spritn10 | Team 4 | T10-006 | Understood and implemented HAProxy setup from a separate EC2 instance to access the application | Elzabeth Lalson | 4 | Done | Trainer
sprint 11 | Team 4 | T11-001 | Gained understanding of API Gateway, Gateway API, and KGateway concepts. Installed and configured KGateway. Successfully exposed the web application using the gateway.. | MUVVALA VENKATA NAGA SAI AKASH | 5 | Done | Trainer
sprint 11 | Team 4 | T11-002 | Gained understanding of API Gateway, Gateway API, and KGateway concepts. Installed and configured KGateway. Successfully exposed the web application using the gateway. | Ashutosh Kumar | 5 | Done | Elzabeth Lalson
sprint 11 | Team 4 | T11-003 | Gained understanding of API Gateway, Gateway API, and KGateway concepts. Installed and configured KGateway. Successfully exposed the web application using the gateway. | M Vignesh | 5 | Done | Trainer
sprint 11 | Team 4 | T11-004 | Gained understanding of API Gateway, Gateway API, and KGateway concepts. Installed and configured KGateway. Successfully exposed the web application using the gateway. | Dhanigasree S | 5 | Done | Dhanigasree
sprint 11 | Team 4 | T11-005 | Gained understanding of API Gateway, Gateway API, and KGateway concepts. Installed and configured KGateway. Successfully exposed the web application using the gateway. | Suwetha Balasundaram | 5 | Done | Trainer
sprint 11 | Team 4 | T11-006 | Gained understanding of API Gateway, Gateway API, and KGateway concepts. Installed and configured KGateway. Successfully exposed the web application using the gateway. | Elzabeth Lalson | 5 | Done | Suwetha Balasundaram
sprint 12 | Team 4 | T12-001 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses | MUVVALA VENKATA NAGA SAI AKASH | 6 | Done | Elzabeth Lalson
sprint 12 | Team 4 | T12-002 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses | Ashutosh Kumar | 6 | Done | Trainer
sprint 12 | Team 4 | T12-003 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses | M Vignesh | 6 | Done | Ashutosh Kumar
sprint 12 | Team 4 | T12-004 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses | Dhanigasree S | 6 | Done | Trainer
sprint 12 | Team 4 | T12-005 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses | Suwetha Balasundaram | 6 | Done | M vignesh
sprint 12 | Team 4 | T12-006 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses | Elzabeth Lalson | 6 | Done | Trainer
Sprint 13 | Team 4 | T13-001 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | MUVVALA VENKATA NAGA SAI AKASH | 7 | Done | Trainer
Sprint 13 | Team 4 | T13-002 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Ashutosh Kumar | 7 | Done | MUVVALA VENKATA NAGA SAI AKASH
Sprint 13 | Team 4 | T13-003 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | M Vignesh | 7 | Done | Trainer
Sprint 13 | Team 4 | T13-004 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Dhanigasree S | 7 | Done | M Vignesh
Sprint 13 | Team 4 | T13-005 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Suwetha Balasundaram | 7 | Done | Trainer
Sprint 13 | Team 4 | T13-006 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Elzabeth Lalson | 7 | Done | Suwetha Balasundaram
Sprint 15 | Team 4 | T14-001 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | MUVVALA VENKATA NAGA SAI AKASH | 7 | Done | Trainer
Sprint 15 | Team 4 | T14-002 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Ashutosh Kumar | 7 | Done | M Vignesh
Sprint 15 | Team 4 | T14-003 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | M Vignesh | 7 | Done | Trainer
Sprint 15 | Team 4 | T14-004 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Dhanigasree S | 7 | Done | Suwetha Balasundaram
Sprint 15 | Team 4 | T14-005 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Suwetha Balasundaram | 7 | Done | Elzabeth Lalson
Sprint 15 | Team 4 | T14-006 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Elzabeth Lalson | 7 | Done | Trainer
Sprint 16 | Team 4 | T15-001 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | MUVVALA VENKATA NAGA SAI AKASH | 7 | Done | Trainer
Sprint 16 | Team 4 | T15-002 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Ashutosh Kumar | 7 | Done | M Vignesh
Sprint 16 | Team 4 | T15-003 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | M Vignesh | 7 | Done | Trainer
Sprint 16 | Team 4 | T15-004 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Dhanigasree S | 7 | Done | Suwetha Balasundaram
Sprint 16 | Team 4 | T15-005 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Suwetha Balasundaram | 7 | Done | Elzabeth Lalson
Sprint 16 | Team 4 | T15-006 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Elzabeth Lalson | 7 | Done | Trainer
Sprint 17 | Team 4 | T16-001 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | MUVVALA VENKATA NAGA SAI AKASH | 7 | Done | Trainer
Sprint 17 | Team 4 | T16-002 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Ashutosh Kumar | 7 | Done | MUVVALA VENKATA NAGA SAI AKASH
Sprint 17 | Team 4 | T16-003 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | M Vignesh | 7 | Done | Trainer
Sprint 17 | Team 4 | T16-004 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Dhanigasree S | 7 | Done | M Vignesh
Sprint 17 | Team 4 | T16-005 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Suwetha Balasundaram | 7 | Done | Trainer
Sprint 17 | Team 4 | T16-006 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Elzabeth Lalson | 7 | Done | Suwetha Balasundaram
Sprint 18 | Team 4 | T17-001 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | MUVVALA VENKATA NAGA SAI AKASH | 7 | Done | Trainer
Sprint 18 | Team 4 | T17-002 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Ashutosh Kumar | 7 | Done | MUVVALA VENKATA NAGA SAI AKASH
Sprint 18 | Team 4 | T17-003 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | M Vignesh | 7 | Done | Trainer
Sprint 18 | Team 4 | T17-004 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Dhanigasree S | 7 | Done | M Vignesh
Sprint 18 | Team 4 | T17-005 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Suwetha Balasundaram | 7 | Done | Trainer
Sprint 18 | Team 4 | T17-006 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Elzabeth Lalson | 7 | Done | Suwetha Balasundaram

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -