## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 4 | MUVVALA VENKATA NAGA SAI AKASH | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Ashutosh Kumar | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | M Vignesh | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Dhanigasree S | DevOps Engineer | Week 1 | No
Batch 1 | Team 4 | Suwetha Balasundaram | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 4 | Elzabeth Lalson | DevOps Engineer | Week 1 | No

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | Deploying a monolithic application | 2013-02-23 | 2020-02-26 | Deploying an app in EC2 instance where web app and backend and Database is deployed in public, private and RDS respectively
Sprint 2 | Deploying a microservices architecture application | 2026-02-25 | 2026-02-26 | Change the app into a micro service architecture and and deploy it using EC2 and RDS
Sprint 3 | Creating our own Docker images using docker build | 2026-02-26 | 2026-02-28 | Creating our own docker image
Sprint 4 | Implemeted multi tier applications across different containers using host gateway | 2026-03-02 | 2026-03-03 | Work in multi tier app using host gateway
Sprint 5 | IImplemeted multi tier applications across different containers using custome network and stored backups using volumes | 2026-03-03 | 2026-03-04 | Work in multi tier app using networks and volumes
Sprint 6 | Familiarised with Docker swarm and with basic of kubernetes | 2026-03-05 | 2026-03-07 | Familiarised with docker swarm and reasons we need kubernetes and with basics of kubernetes
Sprint 7 | Deploying simple pods in cluster | 2026-03-09 | 2026-03-11 | Deploying simple pods in cluster and understand how the response is happening
Sprint 8 | Worked on deploying applications using ReplicaSet, Deployment, and Services; followed manifest rules; implemented rollout and rollback strategies. | 2026-03-12 | 2026-03-14 | Implemented Metrics Server, Horizontal Pod Autoscaler, resource requests and limits; configured ConfigMaps, Secrets, and HAProxy for scaling.
Sprint 9 | Created YAML manifests, successfully deployed applications, validated rollout and rollback functionality, ensured stable and version-controlled deployments. | 2026-03-16 | 2026-03-18 | Enabled auto scaling (scale up/down), configured application settings securely, validated performance, and ensured efficient resource utilization

## Task_Tracking(23-02)
Sprint | Team | TaskID | Description | AssignedTo | StoryPoint | Status | Reviewer
Sprint 1 | Team 4 | T1-001 | Web app deployed properly configuring backend deployment | MUVVALA VENKATA NAGA SAI AKASH | 2 | Done | Trainer
Sprint 1 | Team 4 | T1-002 | Web app deployed properly configuring backend deployment | Ashutosh Kumar | 2 | Done | M Vignesh | Backlog
Sprint 1 | Team 4 | T1-003 | Web app deployed properly configuring backend deployment | M Vignesh | 2 | Done | Trainer
Sprint 1 | Team 4 | T1-004 | Web app deployed properly configuring backend deployment | Dhanigasree S | 2 | Done | Suwetha Balasundaram | To Do
Sprint 1 | Team 4 | T1-005 | Web app deployed properly configuring backend deployment | Suwetha Balasundaram | 2 | Done | Elzabeth Lalson
Sprint 1 | Team 4 | T1-006 | Web app deployed properly configuring backend deployment | Elzabeth Lalson | 2 | Done | Trainer | In Progress
Sprint 2 | Team 4 | T1-007 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | MUVVALA VENKATA NAGA SAI AKASH | 3 | Done | Trainer
Sprint 2 | Team 4 | T1-008 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | Ashutosh Kumar | 3 | Done | M Vignesh | Code Review
Sprint 2 | Team 4 | T1-009 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | M Vignesh | 3 | Done | Trainer
Sprint 2 | Team 4 | T1-010 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | Dhanigasree S | 3 | Done | Suwetha Balasundaram | Done
Sprint 2 | Team 4 | T1-011 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | Suwetha Balasundaram | 3 | Done | Elzabeth Lalson
Sprint 2 | Team 4 | T1-012 | Configuring and Deploying the microservices in the respective EC2 instances and configure the RDS connection | Elzabeth Lalson | 3 | Done | Trainer | Blocked
Sprint 3 | Team 4 | T1-013 | Creating our own Docker images using docker build | MUVVALA VENKATA NAGA SAI AKASH | 4 | Done | Trainer
Sprint 3 | Team 4 | T1-014 | Creating our own Docker images using docker build | Ashutosh Kumar | 4 | Done | M Vignesh
Sprint 3 | Team 4 | T1-015 | Creating our own Docker images using docker build | M Vignesh | 4 | Done | Trainer
Sprint 3 | Team 4 | T1-016 | Creating our own Docker images using docker build | Dhanigasree S | 4 | Done | Suwetha Balasundaram
Sprint 3 | Team 4 | T1-017 | Creating our own Docker images using docker build | Suwetha Balasundaram | 4 | Done | Elzabeth Lalson
Sprint 3 | Team 4 | T1-018 | Creating our own Docker images using docker build | Elzabeth Lalson | 4 | Done | Trainer
Sprint 4 | Team 4 | T1-019 | Setup RDS & Deploy a 3-Tier Monolithic architecture | MUVVALA VENKATA NAGA SAI AKASH | 6 | Done | Trainer
Sprint 4 | Team 4 | T1-020 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Ashutosh Kumar | 6 | Done | M Vignesh
Sprint 4 | Team 4 | T1-021 | Setup RDS & Deploy a 3-Tier Monolithic architecture | M Vignesh | 6 | Done | Trainer
Sprint 4 | Team 4 | T1-022 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Dhanigasree S | 6 | Done | Suwetha Balasundaram
Sprint 4 | Team 4 | T1-023 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Suwetha Balasundaram | 6 | Done | Elzabeth Lalson
Sprint 4 | Team 4 | T1-024 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Elzabeth Lalson | 6 | Done | Trainer
Sprint 5 | Team 4 | T1-025 | Implemeted multi tier applications across different containers using host gateway | MUVVALA VENKATA NAGA SAI AKASH | 3 | Done | Trainer
Sprint 5 | Team 4 | T1-026 | Implemeted multi tier applications across different containers using host gateway | Ashutosh Kumar | 3 | Done | M Vignesh
Sprint 5 | Team 4 | T1-027 | Implemeted multi tier applications across different containers using host gateway | M Vignesh | 3 | Done | Trainer
Sprint 5 | Team 4 | T1-028 | Implemeted multi tier applications across different containers using host gateway | Dhanigasree S | 3 | Done | Suwetha Balasundaram
Sprint 5 | Team 4 | T1-029 | Implemeted multi tier applications across different containers using host gateway | Suwetha Balasundaram | 3 | Done | Elzabeth Lalson
Sprint 5 | Team 4 | T1-030 | Implemeted multi tier applications across different containers using host gateway | Elzabeth Lalson | 3 | Done | Trainer
Sprint 6 | Team 4 | T1-031 | Familiarised with Docker swarm and with basic of kubernetes | MUVVALA VENKATA NAGA SAI AKASH | 4 | Done | Trainer
Sprint 6 | Team 4 | T1-032 | Familiarised with Docker swarm and with basic of kubernetes | Ashutosh Kumar | 4 | Done | M Vignesh
Sprint 6 | Team 4 | T1-033 | Familiarised with Docker swarm and with basic of kubernetes | M Vignesh | 4 | Done | Trainer
Sprint 6 | Team 4 | T1-034 | Familiarised with Docker swarm and with basic of kubernetes | Dhanigasree S | 4 | Done | Suwetha Balasundaram
Sprint 6 | Team 4 | T1-035 | Familiarised with Docker swarm and with basic of kubernetes | Suwetha Balasundaram | 4 | Done | Elzabeth Lalson
Sprint 6 | Team 4 | T1-036 | Familiarised with Docker swarm and with basic of kubernetes | Elzabeth Lalson | 4 | Done | Trainer
Sprint 7 | Team 4 | T1-037 | Deploying simple pods in cluster | MUVVALA VENKATA NAGA SAI AKASH | 5 | Done | Trainer
Sprint 7 | Team 4 | T1-038 | Deploying simple pods in cluster | Ashutosh Kumar | 5 | Done | M Vignesh
Sprint 7 | Team 4 | T1-039 | Deploying simple pods in cluster | M Vignesh | 5 | Done | Trainer
Sprint 7 | Team 4 | T1-040 | Deploying simple pods in cluster | Dhanigasree S | 5 | Done | Suwetha Balasundaram
Sprint 7 | Team 4 | T1-041 | Deploying simple pods in cluster | Suwetha Balasundaram | 5 | Done | Elzabeth Lalson
Sprint 7 | Team 4 | T1-042 | Deploying simple pods in cluster | Elzabeth Lalson | 5 | Done | Trainer
Sprint 8 | Team 4 | T1-043 | Worked on deploying applications using Kubernetes deployment strategie | MUVVALA VENKATA NAGA SAI AKASH | 5 | Done | Elzabeth Lalson
Sprint 8 | Team 4 | T1-044 | Worked on deploying applications using Kubernetes deployment strategie | Ashutosh Kumar | 5 | Done | Suwetha Balasundaram
Sprint 8 | Team 4 | T1-045 | Worked on deploying applications using Kubernetes deployment strategie | M Vignesh | 5 | Done | MUVVALA VENKATA NAGA SAI AKASH
Sprint 8 | Team 4 | T1-046 | Worked on deploying applications using Kubernetes deployment strategie | Dhanigasree S | 5 | Done | Ashutosh Kumar
Sprint 8 | Team 4 | T1-047 | Worked on deploying applications using Kubernetes deployment strategie | Suwetha Balasundaram | 5 | Done | Dhanigasree
Sprint 8 | Team 4 | T1-048 | Worked on deploying applications using Kubernetes deployment strategie | Elzabeth Lalson | 5 | Done | Suwetha Balasundaram
Sprint 9 | Team 4 | T1-049 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | MUVVALA VENKATA NAGA SAI AKASH | 5 | Done | Trainer
Sprint 9 | Team 4 | T1-050 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | Ashutosh Kumar | 5 | Done | Elzabeth Lalson
Sprint 9 | Team 4 | T1-051 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | M Vignesh | 5 | Done | Ashutosh Kumar
Sprint 9 | Team 4 | T1-052 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | Dhanigasree S | 5 | Done | MUVVALA VENKATA NAGA SAI AKASH
Sprint 9 | Team 4 | T1-053 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | Suwetha Balasundaram | 5 | Done | Trainer
Sprint 9 | Team 4 | T1-054 | Implemented configuring HPA metrics scaling ConfigMaps Secrets HAProxy | Elzabeth Lalson | 5 | Done | M vignesh

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -